## Estimate Template
Project Cost Estimate Template
[Company Name]
1500 Bailey Ave | Date: | 2024-03-31
Buffalo NY 14234 | Quote #: | HEALTHSYS-003
https://datasoftlogic.com/home-health-software | Customer ID: | YP-BUFF3905
716-230-9965 | Valid Until: | 2025-05-15
Yash (Project Manager), Lucky(system analyst)
[Customer]
Maria Garrity (Clinic Manager)
file:///C:/Users/04yas/OneDrive%20-%20buffalostate.edu/CIS%20370/healthylife-clinic-project/healthylife-clinic-project/index.html
1300 Elmwood Ave
Buffalo NY 14222
Mariagarrityhealthylife98@gmail.com, +17168783570
Job Description
Design and development of a clinic system for Doctors, Admins, and Patients to manage appointments, records, communication,
and billing with secure access and support features.
Planning Phase 1 - involves gathering requirements, scope, setting project goals, and creating a project plan.
Phase 1 - Planning and Selection | Labor | Materials | Total | Notes
Meetings and Initial Interviews | 1200 | 300 | 1500 | Discussions with doctors, admin, and patient
Scope and Requirements | 1800 | 400 | 2200 | Interactive Sessions to define system requirements
Competitive & Market Research | 900 | 300 | 1200 | Researching existing health clinic system
Hight- Level Project Planing | 500 | 200 | 700 | Timeline, goals, resource allocation, risk overview
0
Subtotal | 4400 | 1200 | 5600 | 5600
Analysis Phase 2 - In this phase, developers go deeper into the requirements gathered during planning, conducting feasibility studies, and defining the scope of the project.
Phase 2 - Systems Analysis | Labor | Materials | Total | Notes
Technical Interviews and Research | 1000 | 300 | 1300 | Backend tech and system compatibility research
Application Solution Design | 1500 | 500 | 2000 | Structure of workflows for doctors/ Admins/ Patients
Use Case & User Flow Development | 1000 | 200 | 1200 | Defines key user interactions and scenarios
Risk & Feasibility Analysis | 700 | 200 | 900 | Assess project risk, timelines, database feasibility
0
Subtotal | 4200 | 1200 | 5400
Design Phase 3 - The design phase focuses on creating the blueprint for the system, including architecture, user interface, database structure, and system specifications.
Phase 3 -Systems Design | Labor | Materials | Total | Notes
Database Development | 1500 | 400 | 1900 | Schema design, relationship, ERD Setup
Programming | 1600 | 400 | 2000 | Backend logic structure and reusable components
Web Design | 1000 | 300 | 1300 | UI Elements, responsive layouts, branding
Final Prototype | 1200 | 300 | 1500 | Clickable mockup with functional interface
Testing | 700 | 300 | 1000 | Design phase testing for early bug fixes and feedback
Subtotal | 6000 | 1700 | 7700 | 7700
Implementation Phase 4 - This is where the actual development and coding of the system takes place, based on the design specifications.
Phase 4 - Implementation | Labor | Materials | Total | Notes
Complete Training | 900 | 200 | 1100 | Training sessions for Admins, Doctors, and Patients
Convert Data, Prep Production Environment | 1000 | 300 | 1300 | Data migration and final environment configuration
0
0
Subtotal | 1900 | 500 | 2400 | 2400
Operations Phase 5 - After the system is deployed, the maintenance and operations phase focuses on addressing any issues, providing updates, and ensuring the system continues to meet user needs.
Phase 5 - Operation and Maintenance | Labor | Materials | Total | Notes
Complete Training | 1000 | 300 | 1300 | Final User training sessions for clinic staff
Convert Data, Prep Production Environment | 1500 | 500 | 2000 | Datamigration and go-live prep for production server
Subtotal | 2000 | 800 | 3300 | 3300
Grand Total: | 18500 | 5400 | 24400 | 24400
Below provide the Critical Path Diagram and Project Duration